## Sheet1
Activity | Description | Schedule 2023 | Budget
Herbicide Spray Program | · Conduct Herbicide Spray Program on project levees to control weed growth | Jan. 22 - Dec. 22 | Calculation | 12 mile length x $1000 / mile
| · Personnel and equipment to include: 2 employees and Airplane |  | Activity Cost | 12000
Rodent Control Program | · Conduct Rodent Control Program on project levees to prevent rodent nesting and tunneling | Jan. 22 - Dec. 22 | Calculation | 12 mile length x $1000 / mile
| · Personnel and equipment to include: 1 employee and pickup truck |  | Activity Cost | 12000
Mowing Program | · Conduct mowing on slopes and roads on project levees to address invasive and other weed growth | Jan. 22 - Dec. 22 | Calculation | 12 mile length x $1,000/ mile
| · Personnel and equipment |  | Activity Cost | 12000
include: 1 employee and 1 Wheel Tractor with mower
Flap Gates Service and repairs | · Conduct maintenance and servicing on flap-gates on levees and channels | Jan. 22 - Dec. 22 | Calculation | Personnel and vehicle cost =
| · Personnel and equipment to include: 1 employee and pickup truck |  |  | 10000
|  |  | Activity Cost | 10000
Gate Repairs Program | · Conduct repairs to gates and fences along project levees and around levee infrastructure | Jan. 22 - Dec. 22 | Calculation | Personnel cost
| · Personnel and equipment to include: 2 employees |  |  | 5000
|  |  | Activity Cost | 5000
Burn Control Program | · Removal of weeds, vegetation along levees and channels for fire prevention/burn control | Jan. 22 - Dec. 22 | Calculation | Personnel and vehicle cost =
| · Personnel and equipment to include: 2 employees and 2 pickup trucks |  |  | 10000
|  |  | Activity Cost | 10000
Grading Repairs Program | · Conduct grading repairs to levee slopes and access roads | Jan. 22 - Dec. 22 | Calculation | Personnel and equipment cost =
|  |  | Activity Cost | 8000
Sand, gravel, shovels, plastic rolls and butons | • Material for flood fighting | Jan. 22 - Dec. 22 | Material | 20000
Sprayer | • Equipment | Jan. 22 - Dec. 22 | Equipment | 10000
Final SWIF | Incorporate USACE Comments on the SWIF | Jan. 22 - Dec. 22 |  | 20000
Technical Study | Technical studies and design work for arresting erosion at various sites | Jan. 22 - Dec. 22 |  | 20000
TOTAL COST |  |  |  | 139000